## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
| Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | AL ¦ 7/16/2024
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | AL ¦ 7/16/2024
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Fail | AL ¦ 7/16/2024 ¦ No message
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | AL ¦ 7/16/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | AL ¦ 7/16/2024 ¦ Auto loggs out when need is selected
As a helper I want to search for a need needs so that I can find a need in the cupboard. | Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs avaiable to search from. | Fail | AL ¦ 7/16/2024 ¦ No message
| Given that I am on the Needs page when there are needs in the cupboard and the name of the need I searched for exists, then I should see the Need appear in detail. | Fail | AL ¦ 7/16/2024 ¦ No search function implemented
| Given that I am on the Needs page when there are needs in the cupboard and the name of the need I searched for doesn't exist, then I should see nothing appear in the search bar. | Fail | AL ¦ 7/16/2024 ¦ No search function implemented
As a helper I want to check out the Funding Basket | Given I am logged in on the Needs page and have needs in my basket when I press the "checkout" button then I should be taken to a checkout page. | Pass | NM ¦ 7/16/2024 ¦ Proceeds to checkout page properly
| Given I am viewing the checkout page when I press a "finalize donation" button then I should be returned to the home page with a now empty funding basket and the cupboard updated to reflect the donation made. | Fail | NM ¦ 7/16/2024 ¦ Does not clear funding basket after clicking finalize
As a helper I want to add a need to my funding basket so that I can save needs for the purpose of it being checked out. | Given that I am on the Needs page and I add an exisitng Need to my funding basket, then I should see the need appear in the funding basket. | Pass | NM ¦ 7/16/2024 ¦ It worked one way, doesn't let me delete a need from basket
As a helper I want to view my funding basket so that I can see what is my funding basket. | Given that I am on the Needs page when there are no needs in the funding basket then I should see an empty funding basket. | Pass | NM ¦ 7/16/2024 ¦ Works, but can't empty funding basket.
| Given that I am on the Needs page when there are needs in the funding basket then I should see a full list of needs in my funding basket | Pass | NM ¦ 7/16/2024 ¦ Works, but can't empty funding basket.
As a helper I want to save my funding basket bewteen logins and logouts so that I can edit my funcing basket whenever I want. | Given that I have added needs to my funding basket and logged out, when I log back in, then I should see the same needs in my funding basket. | Pass | AL ¦ 7/16/2024 ¦ Works but every time a need is added to basket user is logged out
| Given that I haven't added any needs to my funding basket and logged out, when I log back in, then I should an empty funding basket | Pass | AL ¦ 7/16/2024 ¦ Works but every time a need is added to basket user is logged out
As a helper I want to be able to delete a need from the funding basket. | Given that I am on the Funding Basket page and I delete an exisitng Need from my funding basket, then I should see the need disappear from the funding basket. | Fail | GZ ¦ 7/16/2024 ¦ The system logs you out and the full list of the funding basket cannot be seen anymore.
| Given that I am on the Funding Basket page and I delete a Need not present in the Funding Basket from my funding basket, then I should see an error message. | Fail | GZ ¦ 7/16/2024 ¦ Unable to reach the error message on the UI, as you can't see a need that has not been added to the funding basket.
As a manager I want to add a need to my cupboard | Given that I am on the manager page when I add a need to the cupboard, then I should see the need in the cupboard. | Fail | AL ¦ 7/16/2024 ¦ None of the manager functions work
As a Manager, I want to remove needs in my cupboard | Given that I am on the Manager page I delete an existing need, then the need should disappear from the cupboard | Fail | AL ¦ 7/16/2024 ¦ None of the manager functions work
| Given that I am on the Manager page I delete a non-extant need, then an error should be reported | Fail | AL ¦ 7/16/2024 ¦ None of the manager functions work
As a manager I want to edit a need in my cupboard so that incorrect needs are being used. | Given that I am on the manager page when I click on a need, I should can edit the need, so that the need is fixed when I see it back in the cupboard. | Fail | AL ¦ 7/16/2024 ¦ None of the manager functions work